## Sprint 5
Ticket No | User Stories | Assignee | Reporter
EP-97 | As a Manager, I want to view contribution statistics for each faculty so that I can monitor university-wide performance. | Min Khant | Hein Htet Aung
EP-98 | As a Guest, I want to view selected contributions from my assigned faculty so that I can read published articles. | Min Khant | Hein Htet Aung
EP-99 | As an Admin, I want to see which pages are visited most often and which browsers users prefer so that I can understand system adoption. | Min Khant | Hein Htet Aung
EP-100 | As a Tester, I want to execute full regression testing across all five roles so that no previously working feature is broken. | Su Yi Hnin | Hein Htet Aung
EP-101 | As a Tester, I want to complete the test log for all test cases TC01 to TC44 so that testing evidence is ready for the group report. | Su Yi Hnin | Hein Htet Aung
EP-102 | As a Tester, I want to verify responsive design on mobile, tablet, and desktop viewports so that the system meets the responsive design requirement. | Su Yi Hnin | Hein Htet Aung
EP-103 | As a User, I want a dedicated Reports section in the sidebar so that I can quickly navigate to statistical information. | Thet Wai Aung | Hein Htet Aung
EP-104 | As a Guest, I want a read-only dashboard showing selected contributions from my faculty so that I can browse published articles. | Thet Wai Aung | Hein Htet Aung
EP-105 | As an Admin, I want to see browser statistics and page access counts in the admin panel so that I can monitor system usage. | Thet Wai Aung | Hein Htet Aung
EP-106 | As a Documentation Reporter, I want to write the complete Functionality section covering role-based security with code snippets so that the group report meets the 10% Functionality requirement. | Aung Kaung Myat | Hein Htet Aung
EP-107 | As a Documentation Reporter, I want to compile the References section with all cited sources so that the group report meets academic standards. | Aung Kaung Myat | Hein Htet Aung
EP-108 | As a Documentation Reporter, I want to finalise the Table of Contents and section numbering so that the group report is properly structured. | Aung Kaung Myat | Hein Htet Aung
EP-109 | As a Database Designer, I want to perform a security review of all RLS policies and access controls so that the database meets security requirements for the group report. | Su Su Lwin | Hein Htet Aung
EP-110 | As a Database Designer, I want to verify all foreign key constraints and referential integrity across the complete schema so that data consistency is guaranteed. | Su Su Lwin | Hein Htet Aung
EP-111 | As a Database Designer, I want to finalise the ERD and data dictionary for the group report so that the Database section is submission-ready. | Su Su Lwin | Hein Htet Aung
EP-112 | As a Manager, I want analytics charts to remain clear and readable on tablets and mobile devices so that I can review statistics anywhere. | Hein Htet Aung | Hein Htet Aung
EP-113 | As a User, I want all reporting and analytics information to be clearly presented so that I can understand how statistics are produced. | Hein Htet Aung | Hein Htet Aung
EP-114 | As a Product Owner, I want to prepare and record the 10-minute screencast demo so that the system is presented professionally for coursework submission. | Hein Htet Aung | Hein Htet Aung
EP-115 | As a UI/UX Designer, I want to design the guest dashboard with a read-only card layout so that guests can browse selected contributions clearly. | Yan Yan Moe Oo | Hein Htet Aung
EP-116 | As a UI/UX Designer, I want to perform a final UI consistency review across all screens so that spacing, colours, and typography are uniform. | Yan Yan Moe Oo | Hein Htet Aung
EP-117 | As a UI/UX Designer, I want to verify accessibility compliance with ARIA labels and contrast ratios so that the application meets accessibility standards. | Yan Yan Moe Oo | Hein Htet Aung
EP-118 | As a Documentation Reporter, I want to record Sprint 5 meeting minutes so that the final sprint decisions are documented. | Zaw Naing Win | Hein Htet Aung
EP-119 | As a Documentation Reporter, I want to capture the Sprint 5 burndown chart and board screenshot so that all sprints have velocity evidence. | Zaw Naing Win | Hein Htet Aung
EP-120 | As a Documentation Reporter, I want to perform a final review of the complete group report for consistency and completeness so that the submission is ready. | Zaw Naing Win | Hein Htet Aung