## Sprint 3
Ticket No | User Stories | Assignee | Reporter
EP-49 | As a Coordinator, I want to add comments on student contributions so that I can provide feedback within the 14-day deadline. | Min Khant | Hein Htet Aung
EP-50 | As a Coordinator, I want to receive a notification when a student submits a contribution so that I can begin reviewing it promptly. | Min Khant | Hein Htet Aung
EP-51 | As a Coordinator, I want to view and filter contributions within my faculty so that I only see submissions I am responsible for reviewing. | Min Khant | Hein Htet Aung
EP-52 | As a Tester, I want to verify that comments are correctly linked to the right contribution and student so that feedback history is accurate. | Su Yi Hnin | Hein Htet Aung
EP-53 | As a Tester, I want to verify that contributions without feedback after 14 days are flagged as overdue so that the comment deadline rule is enforced. | Su Yi Hnin | Hein Htet Aung
EP-54 | As a Tester, I want to verify that Coordinators can only access contributions from their assigned faculty so that data privacy is maintained. | Su Yi Hnin | Hein Htet Aung
EP-55 | As a Coordinator, I want an inbox-style view of new submissions with colour-coded countdown indicators so that I can prioritise urgent reviews. | Thet Wai Aung | Hein Htet Aung
EP-56 | As a Coordinator, I want to view a student's submission beside a comment panel so that I can review and provide feedback efficiently. | Thet Wai Aung | Hein Htet Aung
EP-57 | As a Coordinator, I want submission notifications to be clear and professional so that I can trust the message and access the contribution quickly. | Thet Wai Aung | Hein Htet Aung
EP-58 | As a Documentation Reporter, I want to document the 14-day comment rule implementation with code snippets so that the Functionality section explains the business logic. | Aung Kaung Myat | Hein Htet Aung
EP-59 | As a Documentation Reporter, I want to document the email notification system so that the group report covers how Coordinators are alerted to new submissions. | Aung Kaung Myat | Hein Htet Aung
EP-60 | As a Documentation Reporter, I want to write user stories for Sprint 3 features so that the product backlog is updated. | Aung Kaung Myat | Hein Htet Aung
EP-61 | As a Database Designer, I want to design the Comments table with foreign keys to Contributions so that feedback is correctly associated with submissions. | Su Su Lwin | Hein Htet Aung
EP-62 | As a Database Designer, I want to create the database view for contributions without comments so that the 14-day exception report can be generated efficiently. | Su Su Lwin | Hein Htet Aung
EP-63 | As a Database Designer, I want to create the database view for contributions without comments after 14 days so that overdue reviews are identifiable. | Su Su Lwin | Hein Htet Aung
EP-64 | As a Coordinator, I want to change a contribution's status so that I can manage the review process correctly. | Hein Htet Aung | Hein Htet Aung
EP-65 | As a Coordinator, I want the dashboard to refresh when new submissions arrive so that I am aware of incoming contributions. | Hein Htet Aung | Hein Htet Aung
EP-66 | As a Coordinator, I want to access only the contributions from my own faculty so that student information from other faculties remains protected. | Hein Htet Aung | Hein Htet Aung
EP-67 | As a UI/UX Designer, I want to design the coordinator dashboard layout with summary cards so that total submissions and pending feedback are visible at a glance. | Yan Yan Moe Oo | Hein Htet Aung
EP-68 | As a UI/UX Designer, I want to design the review panel with document preview and comment thread so that the feedback workflow is intuitive. | Yan Yan Moe Oo | Hein Htet Aung
EP-69 | As a UI/UX Designer, I want to design visual deadline indicators with colour-coded urgency levels so that overdue contributions stand out. | Yan Yan Moe Oo | Hein Htet Aung
EP-70 | As a Documentation Reporter, I want to record Sprint 3 meeting minutes so that team decisions about the coordinator workflow are documented. | Zaw Naing Win | Hein Htet Aung
EP-71 | As a Documentation Reporter, I want to document the coordinator review workflow with sequence diagrams so that the Functionality section includes UML evidence. | Zaw Naing Win | Hein Htet Aung
EP-72 | As a Documentation Reporter, I want to capture the Sprint 3 burndown chart and board screenshot so that sprint progress is recorded. | Zaw Naing Win | Hein Htet Aung